## Summary
Part | Total | Done | In Progress | To Do | Blocked | % Complete
Part 1 | 19 | 19 | 0 | 0 | 0 | 100%
Part 2 | 32 | 32 | 0 | 0 | 0 | 100%
Part 3 | 19 | 19 | 0 | 0 | 0 | 100%
Part 4 | 20 | 20 | 0 | 0 | 0 | 100%
Docs | 14 | 14 | 0 | 0 | 0 | 100%
Quality | 5 | 5 | 0 | 0 | 0 | 100%
TOTAL | 109 | 109 | 0 | 0 | 0 | 100%
Generated | 2026-09-25 22:22:21 India Standard Time
Source | scripts/checklist_data.py (regenerate with scripts/generate_checklist.py)

## Checklist
# | Done | Part | Requirement (from README.md) | Status | Evidence | Notes / Assumptions
PART 1
1 | ✔ | Part 1: Models | Use 3 different models (classification, detection, + similarity search) | DONE | models/registry.json; python -m models.registry list | resnet50 (classification), yolov8n (detection), resnet50-embed (similarity). All three verified serving real predictions.
2 | ✔ | Part 1: Models | Image classification model (ViT / ResNet / EfficientNet) | DONE | models/training/train_classifier.py; scripts/prepare_models.py | ResNet-50 for serving (ImageNet-1k) plus a Tiny-ImageNet fine-tuning pipeline.
3 | ✔ | Part 1: Models | Object detection model (YOLO / DETR) on COCO subset | DONE | scripts/prepare_models.py; models/artifacts/yolov8n.onnx | YOLOv8n trained on COCO. Verified on a real photo: detected 4 people + 1 bus with correct boxes in original image coordinates.
4 | ✔ | Part 1: Models | Fine-tune classifier with MIXED PRECISION | DONE | models/training/train_classifier.py | torch.autocast + GradScaler on CUDA; bf16 on CPU (no scaler needed, since bf16 has float32 exponent range so gradients cannot underflow). Active in the full 60-epoch A100 run: 77.66% top-1 / 91.52% top-5, validated 8/8 by validate.py.
5 | ✔ | Part 1: Models | Fine-tune classifier with GRADIENT CLIPPING | DONE | models/training/train_classifier.py | clip_grad_norm_ after unscaling (order matters with AMP). Grad norm logged per epoch; 8 of 60 epochs hit non-finite grads, absorbed by GradScaler as designed.
6 | ✔ | Part 1: Models | Fine-tune classifier with LEARNING RATE SCHEDULING | DONE | models/training/train_classifier.py | Cosine with linear warmup (default), plus onecycle/step/plateau. Per-batch vs per-epoch stepping handled explicitly. Cosine + 5% warmup over the full 60-epoch run.
7 | ✔ | Part 1: Models | Use the tiny-ImageNet dataset for classification fine-tuning | DONE | data/tiny-imagenet-200; models/training/dataset.py | 200 classes / 120k images downloaded. Custom val loader reads val_annotations.txt, because ImageFolder silently mislabels that split (the provided starter script has this bug).
8 | ✔ | Part 1: Models | Implement custom data augmentation pipeline | DONE | models/training/augmentation.py | Hand-written RandAugment (13 ops), RandomResizedCrop, RandomErasing, MixUp, CutMix.
9 | ✔ | Part 1: Optimisation | Apply INT8 quantization to all models | DONE | models/optimization/quantize.py; benchmarks/reports/quantization.json | All 3 models quantized. resnet50 97.4->24.5 MB (3.97x), yolov8n 12.2->3.3 MB (3.67x), resnet50-embed 89.6->22.6 MB (3.97x).
10 | ✔ | Part 1: Optimisation | Convert models to ONNX format | DONE | models/optimization/export_onnx.py | All 3 exported and numerically verified against PyTorch (max abs diff < 4e-6). Uses the legacy exporter: torch 2.9's dynamo path ignored dynamic_axes (breaking batching) and split weights into a sidecar file.
11 | ✔ | Part 1: Optimisation | Convert models to TensorRT format | DONE | models/optimization/export_tensorrt.py; benchmarks/reports/BENCHMARKS_GPU.md | EXECUTED on an A100 (TensorRT 11.3.0.99). All three precisions built and verified: int8 0.920 ms p50, 1068 img/s, 24.1 MB; fp16 0.990 ms, 1066 img/s, 46.0 MB; fp32 1.298 ms, 822 img/s, 91.5 MB. Handles the TRT 8/10/11 API differences by probing attributes. INT8 needed a separate QDQ graph: fp32 biases, symmetric, percentile calibration, stem conv excluded.
12 | ✔ | Part 1: Optimisation | Benchmark inference times across all formats | DONE | benchmarks/reports/BENCHMARKS.md | fp32 ONNX vs INT8 static, batch 1 and 4, all 4 models, p50/p95/p99 with environment recorded, plus fp32/fp16/int8 TensorRT engines on an A100. Key findings: dynamic INT8 will not load as configured (uint8 activations against int8 weights is not a registered ConvInteger kernel; QUInt8 weights fix it), static QDQ is 1.07x to 2.30x slower depending on the model and 3.9x smaller, and on GPU int8 matches fp16 on latency while halving engine size.
13 | ✔ | Part 1: Validation | Comprehensive model validation pipeline | DONE | models/validation/validate.py | 8 checks: artifacts, determinism, batch invariance, output sanity, robustness, accuracy, calibration (ECE), latency. Caught 2 real bugs during development.
14 | ✔ | Part 1: Validation | A/B testing framework for model comparison | DONE | models/validation/ab_test.py | Paired McNemar test, confidence interval on the accuracy delta, deterministic hash-based traffic splitting, and required-sample-size guidance.
15 | ✔ | Part 1: Validation | Model drift detection using statistical tests | DONE | models/validation/drift.py | KS test, chi-square and PSI. Requires BOTH significance and a meaningful effect size, so a large sample cannot produce alert spam. Verified on a 200k-sample case.
16 | ✔ | Part 1: Validation | Performance regression testing | DONE | models/validation/regression.py | Baseline store with per-metric tolerances (absolute for accuracy, relative for latency) and hardware fingerprinting. Verified it catches an injected 150% regression.
17 | ✔ | Part 1: Deliverable | models/ directory with training scripts and model artifacts | DONE | models/ | training/, optimization/, validation/, cards/, artifacts/, registry.py
18 | ✔ | Part 1: Deliverable | benchmarks/ directory with performance comparison reports | DONE | benchmarks/reports/ | BENCHMARKS.md, benchmark_results.json, quantization.json, validation.json
19 | ✔ | Part 1: Deliverable | Comprehensive model cards with metrics and limitations | DONE | models/cards/ | One card per model: architecture rationale, measured latency, validation results, and an explicit limitations section (bias, calibration, scaling, licensing).
PART 2
20 | ✔ | Part 2: Structure | FastAPI app structure exactly as specified in README | DONE | api/ | Matches the README tree. Added api/dependencies.py (shared FastAPI dependencies) and api/config.py, both documented in the README.
21 | ✔ | Part 2: Structure | api/main.py | DONE | api/main.py | App factory, lifespan, middleware stack, custom OpenAPI.
22 | ✔ | Part 2: Structure | api/routers/classification.py | DONE | api/routers/classification.py | JSON + multipart variants.
23 | ✔ | Part 2: Structure | api/routers/detection.py | DONE | api/routers/detection.py | JSON + multipart variants.
24 | ✔ | Part 2: Structure | api/models/schemas.py | DONE | api/models/schemas.py | Request schemas + shared enums.
25 | ✔ | Part 2: Structure | api/models/responses.py | DONE | api/models/responses.py | Response schemas for every endpoint.
26 | ✔ | Part 2: Structure | api/services/model_service.py | DONE | api/services/model_service.py | Registry, version resolution, ONNX/Torch/TensorRT runtimes, cached thread-safe loading.
27 | ✔ | Part 2: Structure | api/services/cache_service.py | DONE | api/services/cache_service.py | Redis result cache; fails soft to cache-miss when Redis is down (verified).
28 | ✔ | Part 2: Structure | api/services/inference_service.py | DONE | api/services/inference_service.py | Orchestration, softmax/NMS, concurrency semaphore, timeouts, fallbacks.
29 | ✔ | Part 2: Structure | api/middleware/auth.py | DONE | api/middleware/auth.py | API key + JWT. Verified: valid key 200, bad key 401, no key 401.
30 | ✔ | Part 2: Structure | api/middleware/rate_limit.py | DONE | api/middleware/rate_limit.py | Redis Lua token bucket, per-tier. Verified: 3 rpm allows 3, blocks the 4th.
31 | ✔ | Part 2: Structure | api/middleware/monitoring.py | DONE | api/middleware/monitoring.py | Correlation IDs, request logging, Prometheus counters/histograms.
32 | ✔ | Part 2: Structure | api/utils/image_processing.py | DONE | api/utils/image_processing.py | Decode, EXIF fix, centre-crop + letterbox resize, normalise, box un-letterboxing.
33 | ✔ | Part 2: Structure | api/utils/validators.py | DONE | api/utils/validators.py | Size/format/dimension/bomb checks + SSRF guard on image_url.
34 | ✔ | Part 2: Endpoints | POST /api/v1/classify | DONE | api/routers/classification.py | Verified 200 with real predictions.
35 | ✔ | Part 2: Endpoints | POST /api/v1/detect | DONE | api/routers/detection.py | Verified 200, 5 objects detected.
36 | ✔ | Part 2: Endpoints | POST /api/v1/batch | DONE | api/routers/batch.py | 202 + job id; Celery worker; poll/cancel endpoints.
37 | ✔ | Part 2: Endpoints | GET /api/v1/models | DONE | api/routers/models.py | Verified: 3 models with defaults per task.
38 | ✔ | Part 2: Endpoints | GET /api/v1/health | DONE | api/routers/health.py | Plus /health/live and /health/ready probes.
39 | ✔ | Part 2: Endpoints | GET /api/v1/metrics (Prometheus) | DONE | api/routers/metrics.py | Verified: Prometheus text format returned.
40 | ✔ | Part 2: Features | Rate limiting with different limits per user tier | DONE | api/middleware/rate_limit.py | free 10 / basic 60 / pro 300 / enterprise 3000 rpm. Batch costs N tokens.
41 | ✔ | Part 2: Features | Comprehensive image validation (size, format, content) | DONE | api/utils/validators.py | Verified: empty, garbage, truncated, disallowed format, bomb, SSRF all rejected.
42 | ✔ | Part 2: Features | Async processing: background jobs for large batch requests | DONE | worker/celery_app.py, worker/tasks.py, api/routers/batch.py | Celery + Redis. One bad image fails only its own item, never the batch.
43 | ✔ | Part 2: Features | Model versioning: support multiple model versions | DONE | api/services/model_service.py, models/registry.py | Pin model_name/model_version per request, or 'latest'. POST /models/reload picks up new versions live.
44 | ✔ | Part 2: Features | Graceful degradation: fallback when models fail | DONE | api/services/inference_service.py | Runtime fallback chain + model fallback with degraded:true. A typo'd model name correctly returns 404 rather than silently serving a different model.
45 | ✔ | Part 2: Errors | Structured logging with correlation IDs | DONE | api/logging_config.py | JSON logs, contextvar correlation id, returned as X-Correlation-ID (verified).
46 | ✔ | Part 2: Errors | Custom exception handling with user-friendly messages | DONE | api/exceptions.py | One error envelope. Verified: 400/401/404/413/415/422/429/503 all correct shape.
47 | ✔ | Part 2: Errors | Request/response logging for debugging | DONE | api/middleware/monitoring.py | One structured line per request.
48 | ✔ | Part 2: Errors | Performance monitoring and alerting | DONE | monitoring/prometheus/alerts.yml; monitoring/grafana/ | 15 Prometheus metrics (counters, histograms, gauges) covering requests, inference, cache, model loads and batch jobs. 11 alert rules validated by promtool, each alerting on a user-visible symptom rather than a cause and carrying a description of what to do about it. 22-panel Grafana dashboard, auto-provisioned. All VERIFIED live against the running stack.
49 | ✔ | Part 2: Deliverable | Complete FastAPI application with all endpoints | DONE | api/main.py | 18 documented paths. Verified live through the Docker stack.
50 | ✔ | Part 2: Deliverable | Comprehensive API documentation (auto-generated + custom) | DONE | docs/API.md + /docs + /redoc | Auto-generated OpenAPI enriched with auth, rate limits and the error envelope, plus a hand-written reference.
51 | ✔ | Part 2: Deliverable | Postman collection or OpenAPI spec for testing | DONE | docs/openapi.json | OpenAPI 3.1, 18 paths / 37 schemas. Importable directly into Postman.
PART 3
52 | ✔ | Part 3: Unit | Unit tests, target >90% coverage | DONE | tests/unit/ | 95.9% across api/ and worker/ together, the request path end to end: 95.7% on api/, 100% on worker/. 89.3% repo-wide including the training and MLOps code. The async batch endpoint was the last gap at 82.6% and is now fully covered, including the URL fetch with its SSRF checks, the soft-timeout partial-results path and the completion callback at both the helper and its call site.
53 | ✔ | Part 3: Unit | Test model inference functions | DONE | tests/unit/test_inference_service.py | softmax, NMS, L2-norm, all 3 tasks.
54 | ✔ | Part 3: Unit | Test image preprocessing utilities | DONE | tests/unit/test_image_processing.py | 27 tests including EXIF orientation, alpha compositing, letterbox round-trip.
55 | ✔ | Part 3: Unit | Test API route handlers | DONE | tests/unit/test_api_routes.py | 51 tests across every endpoint.
56 | ✔ | Part 3: Unit | Test service layer functions | DONE | tests/unit/ | model, cache, inference and similarity-index services.
57 | ✔ | Part 3: Unit | Mock external dependencies | DONE | tests/conftest.py | fakeredis, aiosqlite and a FakeRuntime, so the suite needs no running services.
58 | ✔ | Part 3: Integration | Test database operations | DONE | tests/integration/test_database.py | 20 tests against real SQL (SQLite).
59 | ✔ | Part 3: Integration | Test model loading and inference | DONE | tests/integration/test_model_loading.py | 25 tests against the real ONNX artifacts.
60 | ✔ | Part 3: Integration | Test API endpoint integration | DONE | tests/unit/test_api_routes.py, tests/integration/, scripts/smoke_test_api.py | Plus a verified live run through the Docker stack: 30 checks over every documented endpoint, 30/30 through the gateway and 30/30 against the API's own port. It is a script rather than a transcript, so it reruns against any deployment and exits non-zero on a failure.
61 | ✔ | Part 3: Performance | Stress testing for model inference | DONE | tests/performance/test_performance.py, tests/performance/locustfile.py | Concurrency, sustained load and throughput; locust for HTTP-level load.
62 | ✔ | Part 3: Performance | Memory usage profiling | DONE | tests/performance/test_performance.py | Verified memory levels off over 100 inferences rather than growing linearly.
63 | ✔ | Part 3: Infra | Pytest configuration with fixtures | DONE | pytest.ini, tests/conftest.py
64 | ✔ | Part 3: Infra | Test database setup/teardown | DONE | tests/conftest.py | Fresh in-memory DB per test.
65 | ✔ | Part 3: Infra | Mock services for external dependencies | DONE | tests/conftest.py
66 | ✔ | Part 3: Infra | Continuous testing with GitHub Actions | DONE | .github/workflows/ci.yml
67 | ✔ | Part 3: Deliverable | tests/ directory with complete test suite | DONE | tests/ | 366 tests: unit, integration and performance.
68 | ✔ | Part 3: Deliverable | Test configuration and fixtures | DONE | tests/conftest.py
69 | ✔ | Part 3: Deliverable | Performance test reports | DONE | benchmarks/reports/
70 | ✔ | Part 3: Deliverable | CI/CD pipeline configuration | DONE | .github/workflows/ci.yml | Eight jobs: lint, tests on 3.11 and 3.12, security scan, image build, end-to-end against the deployed stack, real model export. Plus release.yml (publishes attested, scanned images on a version tag) and drift-watch.yml (weekly retraining decision, verified by a manual run).
PART 4
71 | ✔ | Part 4: Docker | Multi-stage builds for optimal image size | DONE | Dockerfile, docker/Dockerfile.worker, docker/Dockerfile.gpu | Builder stage keeps compilers out of the runtime image. A third Dockerfile builds the CUDA/TensorRT serving image.
72 | ✔ | Part 4: Docker | Security best practices (non-root user, minimal base) | DONE | docker/ | Non-root uid 10001, slim base, no-new-privileges, read-only rootfs in production.
73 | ✔ | Part 4: Docker | Optimised for layer caching | DONE | docker/ | Dependencies installed before application code is copied.
74 | ✔ | Part 4: Docker | Separate images for different services | DONE | docker/ | api, worker and gateway built separately.
75 | ✔ | Part 4: Compose | Service: api-gateway (Nginx or Traefik) | DONE | docker/nginx/ | Nginx: least_conn balancing, edge rate limits, /metrics restricted to internal ranges. VERIFIED healthy.
76 | ✔ | Part 4: Compose | Service: ml-api (FastAPI) | DONE | docker-compose.yml | VERIFIED healthy; served real predictions through the gateway.
77 | ✔ | Part 4: Compose | Service: worker (Celery) | DONE | docker-compose.yml | VERIFIED healthy; processed a real 4-image batch (3 ok, 1 bad image isolated).
78 | ✔ | Part 4: Compose | Service: redis | DONE | docker-compose.yml | VERIFIED healthy; cache hits confirmed live.
79 | ✔ | Part 4: Compose | Service: postgres | DONE | docker-compose.yml | VERIFIED healthy.
80 | ✔ | Part 4: Compose | Service: prometheus | DONE | monitoring/prometheus/ | VERIFIED scraping ml-api; 11 alert rules validated by promtool.
81 | ✔ | Part 4: Compose | Service: grafana (optional) | DONE | monitoring/grafana/ | VERIFIED: datasource and 22-panel dashboard auto-provisioned.
82 | ✔ | Part 4: Config | Environment-based configuration | DONE | api/config.py, .env.example | Pydantic Settings; refuses to start insecure in staging/production.
83 | ✔ | Part 4: Config | Health checks for all services | DONE | docker-compose.yml | All 7 report healthy. Liveness deliberately checks no dependencies.
84 | ✔ | Part 4: Config | Proper resource limits | DONE | docker-compose.yml + docker-compose.prod.yml | CPU and memory limits plus reservations per service.
85 | ✔ | Part 4: Config | Volume management for persistent data | DONE | docker-compose.yml | Named volumes; model artifacts mounted read-only.
86 | ✔ | Part 4: Config | Network configuration and service discovery | DONE | docker-compose.yml | Three segmented networks; DNS-based discovery, no hardcoded IPs.
87 | ✔ | Part 4: Deliverable | Dockerfile for each service | DONE | docker/
88 | ✔ | Part 4: Deliverable | docker-compose.yml for local development | DONE | docker-compose.yml | VERIFIED: all 7 services healthy.
89 | ✔ | Part 4: Deliverable | docker-compose.prod.yml for production | DONE | docker-compose.prod.yml | Replicas, no exposed ports, read-only rootfs, secrets required (verified it refuses to start without them).
90 | ✔ | Part 4: Deliverable | Documentation for deployment and scaling | DONE | docs/DEPLOYMENT.md, k8s/README.md | First run, production checklist, scaling guide with measured sizing, a Kubernetes section covering when to move, prerequisites, what changes from Compose and how to verify it, then monitoring, model rollout/rollback, troubleshooting, backup and recovery. The manifests have their own README with the cluster evidence.
DOCS
91 | ✔ | Docs | README: Architecture overview and design decisions | DONE | README.md + docs/TECHNICAL.md | A diagram per deployment target, Compose and Kubernetes, with the middleware ordering rationale and layering. TECHNICAL.md §6 covers why the cluster topology differs: HPA instead of a typed replica count, ingress instead of the gateway container, fetched rather than baked-in artifacts, and migrations in an init container.
92 | ✔ | Docs | README: Setup and installation instructions | DONE | README.md | 4-step quick start, verified from a clean state.
93 | ✔ | Docs | README: API usage examples | DONE | README.md, docs/API.md | curl examples with real responses.
94 | ✔ | Docs | README: Performance benchmarks | DONE | README.md, benchmarks/reports/BENCHMARKS.md | Measured on named hardware, reproducible with one command.
95 | ✔ | Docs | README: Known limitations and future improvements | DONE | README.md, docs/ASSUMPTIONS.md | 6 limitations stated plainly; 6 prioritised next steps.
96 | ✔ | Docs | API docs: Complete endpoint documentation | DONE | docs/API.md | Every endpoint, all parameters.
97 | ✔ | Docs | API docs: Request/response examples | DONE | docs/API.md | Real captured responses, not invented ones.
98 | ✔ | Docs | API docs: Error handling guide | DONE | docs/API.md | All 14 error codes with retry guidance.
99 | ✔ | Docs | API docs: Authentication guide | DONE | docs/API.md | API key and JWT, with failure modes.
100 | ✔ | Docs | Technical doc: Model selection and optimisation rationale | DONE | docs/TECHNICAL.md | Why each model, what was traded away, and the INT8 finding in full.
101 | ✔ | Docs | Technical doc: Performance benchmarking results | DONE | docs/TECHNICAL.md | Latency, batching, load test, verified system properties.
102 | ✔ | Docs | Technical doc: System architecture decisions | DONE | docs/TECHNICAL.md | 7 decisions with reasoning, including the three different failure policies.
103 | ✔ | Docs | Technical doc: Scalability considerations | DONE | docs/TECHNICAL.md | What scales, what does not (the similarity index), sizing from measurement.
104 | ✔ | Docs | Documented assumptions | DONE | docs/ASSUMPTIONS.md | Brief ambiguities, gaps stated plainly, 3 bugs found in the provided scaffolding and 8 found in my own work.
QUALITY
105 | ✔ | Quality | PEP 8 compliance, type hints, docstrings | DONE | pyproject.toml; ruff + black clean | Ruff (13 rule groups) and black pass with zero findings. Every module, class and public function has a docstring explaining WHY, not just what. Each disabled lint rule carries a written reason.
106 | ✔ | Quality | Test coverage minimum 85% for critical paths | DONE | pytest --cov | Zero modules below 85% on the critical path, counting worker/ as well as api/: 95.9% across the two, 95.7% on api/, 100% on worker/tasks.py and worker/celery_app.py. 89.3% across the whole repo. The weakest critical-path module is health.py at 86.8%. What remains under 85% is training and MLOps code no request touches: registry.py (a CLI, not imported by api/ or worker/), train_classifier.py, retraining.py, dataset.py, tracking.py.
107 | ✔ | Quality | Performance: sub-second inference for single images | DONE | benchmarks/reports/BENCHMARKS.md | p99 at batch 1: resnet50 146ms, resnet50-tiny-imagenet 93ms, yolov8n 166ms, embed 63ms. Every model and both precisions stay inside the 1s budget; the slowest overall is yolov8n INT8 at 338ms, 3x inside it.
108 | ✔ | Quality | Security: no hardcoded secrets, proper input validation | DONE | api/config.py, api/utils/validators.py | Fails closed on auth; production refuses to start without secrets (verified). SSRF guard, decompression-bomb guard, magic-byte format detection, TorchScript not pickle, JWT algorithm pinning.
109 | ✔ | Quality | Scalability: design for horizontal scaling | DONE | k8s/, docs/TECHNICAL.md, docker-compose.prod.yml | Stateless API, Redis-backed distributed rate limiting, independent worker scaling, and a pgvector-backed similarity index shared by every replica (the per-process default does not scale, which is why the Kubernetes config sets SIMILARITY_BACKEND=pgvector). Verified on a kind cluster: the HPA scaled ml-api from 1 pod to 2 under a forced target.